## 2
PROJECT: AUTOMATED PETROL PUMP
Project Plan
WEEK
# | Activity | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
1 | Finalized team | 1 | 2
2 | Dicussed idea with the advisor | 2 | 3
3 | Developed meeting format | 4 | 4
4 | Methadology For Project: Planning | 5 | 7
5 | Literature Review | 7 | 10
6 | Layout of project | 9 | 11
7 | Learning Arduino IDE | 10 | 14
8 | Allocate Budget | 14 | 15
9 | Researching and buying the components | 13 | 18
10 | Learning latex | 18 | 19
11 | FYP-1 report | 12 | 21
12 | learning Nextion Editor | 20 | 26
13 | Designing model on Nextion Editor | 23 | 28
14 | implementation of alogorithm on arduino | 24 | 31
15 | Interfacing Nextion with Arduino | 27 | 32
16 | implementation of Circuit Diagram | 29 | 34
17 | Testing and Trobleshoot | 34 | 36
18 | Making modifications | 35 | 37
19 | References and Diagrams | 37 | 39
20 | Presentation Slides | 39 | 40
21 | FYP-II report | 27 | 40
group work
Rajesh
Umair Ali
Asad and Usama
Rajesh and Umair