## Sheet1
|  |  |  | A Bipedal Walking Robot | [21 empty] | Awais Murtza ID#14019019124
Muhammad bin tariq ID#14019019133
Mohamad Mohsion ID#14019019139
Yahya Naseem ID#14019019044
Activity | Weeks
| june -w1 | june -w2 | june-w3 | june-w4 | july-w1 | july-w2 | july-w3 | july-w4 | Aug-w1 | Aug-w2 | Aug-w3 | Aug-w4 | Sep-w1 | Sep-w2 | Sep-w3 | Sep-w4 | Oct-w1 | Oct-w2 | Oct-w3 | Oct-w4 | Nov-w1 | Nov-w2 | Nov-w3 | Nov-w4 | Dec-w1 | Dec-w2 | Dec-w3 | Dec-w4 | jan-w1 | jan-w2 | jan-w3 | jan-w4 | feb-w1 | feb-w2 | feb-w3 | feb-w4 | mar-w1 | mar-w2 | mar-w3 | mar-w4 | apr-w1 | apr-w2 | apr-w3 | apr-w4 | may-w1 | may-w2 | may-w3 | may-w4 | june-w1 | june-w2 | june-w3 | june-w4
Finalize Team And Advisor
Discussing ideas with advisor and team | bar: june-w3
Project Launch | bar: june-w3
Methadology For Project: Planning | bar: june-w4
Develop Meeting Format | bar: july-w1
Review Past Designs And search Components | bar: july-w2
Litrature review from IEEE papers | bar: july-w2 to Aug-w1
Explore books on bi-pedal and robotics | bar: Aug-w1
Comparing walking techniques and selecting one | bar: Aug-w2
For controller selection meeting with Makistan(ITU) | bar: Aug-w2 to Aug-w3
Meeting with Lect.Usama Bin Sikandar(ITU)(MS-Control systems form geogia tech university) | bar: Aug-w2 to Aug-w3
Meeting with DIY Space CEO | bar: Aug-w2 to Aug-w3
Allocate Budget | bar: Aug-w4
Hardware Selection | bar: Aug-w4 to Sep-w2
Making Basic Prototype 3 degrees | bar: Sep-w3 to Oct-w2
Interfacing 3 degrees of freedom using ADXL | bar: Sep-w3 to Oct-w2
Serial communication between arduino and computer | bar: Sep-w4
Testing and Troubleshoot the errors | bar: Sep-w3 to Oct-w2
Analysing the results usning sensory feedback | bar: Oct-w2 to Oct-w3
Tests to make it precise | bar: Oct-w3
Fyp-1 Report on the basis of 3 degrees | bar: Oct-w3 to Nov-w3
Study of different walking styles | bar: Nov-w4 to Dec-w1
Understanding Mechanism of Walking | bar: Nov-w4 to Dec-w1
Understanding the concept of ZMP | bar: Dec-w1 to Dec-w2
Walking control alogorithm and design | bar: Dec-w1 to Dec-w2
Basic theorey for calculation of ZMP | bar: Dec-w1 to Dec-w2
Types of Hardware design of Bi-pedal | bar: Aug-w2 to Aug-w3
Selecting and purchasing hardware | bar: Aug-w4 to Sep-w1
Hardware assembeling | bar: Dec-w3 to jan-w2
Hardware testing | bar: Dec-w3 to jan-w2
Serial and bluetooth communication between arduino and computer for 10 degrees | bar: jan-w2 to jan-w3
First Standing code | bar: jan-w3 to jan-w4
Code to bring Robot on standing condition from lying on floor | bar: jan-w4 to feb-w2
First attempt for walking | bar: jan-w4 to feb-w2
PID algorithm by shifting and controlling speed of motors | bar: feb-w2 to feb-w3
Code to kick the ball | bar: feb-w3 to mar-w1
Code to take turn | bar: feb-w4 to mar-w2
Code to prove stability by full leg flip | bar: feb-w4 to mar-w2
Manual/physical feedback to improve walking | bar: feb-w1 to may-w2
Finally code for walking in chunks | bar: mar-w2 to june-w2
Testing And Troubleshoot | bar: jan-w2 to may-w3
Shifting it from serial to bluetooth | bar: may-w3 to june-w2
Final Design Completion | bar: may-w1 to june-w1
Testing Functionality | bar: may-w2 to june-w2
Presentation Slides | bar: june-w3 to june-w4
Literature review And References | bar: apr-w3 to may-w4
Diagrams | bar: may-w3 to may-w4
Summary of project | bar: jan-w2 to feb-w1; mar-w1 to mar-w3; june-w2
Bi-weakly student meetings record------ with dates and tasks
Fyp-2 Report | bar: apr-w4 to june-w4
| Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
Legend:
Group Work
Awais Murtza
Muhammad Bin Tariq
Muhammad Mohsin
Yahya Naseem
Awais and Muhammad
Muhammad and Mohsin
Awais,Muhammad and Mohsin
Muhammad,Mohsin and Yahya
Awais and Mohsin
Mohsin and Yahya
Total No. of Testings of Robot =250
Muhammad=100
Awais =100
Mohsin=40
Yahya=10
| Column1: Hall road | Body Assembling =52
| Column1: Awais =3 | Mohsin=52
| Column1: Muhammad=5 | Muhammad=40
| Column1: Mohsin=5 | Awais=30
| Column1: Yahya=1 | Yahya=20