Exploring the Risk Factor Associated with Pre-Engineered Building Projects In Lahore.

A Project submitted in partial fulfillment of the requirement for the degree of Master of Science in Project Management at School of Professional Advancement, University of Management and Technology Lahore

Submitted by:

Rizwan Khurram
MS PM 13001171-010

Approved Supervisor:      			               Approved Co-Supervisor:

Name:  Mr. Talha Zubair                                               Name: Mr. Syed Ali Bukhari

Signature: ____________________                              Signature: ____________________

Dated: _______________________                              Dated: _______________________

School of Professional Advancement

Exploring the Risk Factor Associated with Pre-Engineered Building Projects In Lahore.

Submitted by:

Rizwan Khurram
MS PM 13001171-010

SCHOOL OF PROFESSIONAL ADVANCEMENT

UNIVERSITY OF MANAGEMENT AND TECHNOLOGY

2017

Acknowledgements

All praises to Allah Almighty the Lord, the superior, the creator of everything, the most Beneficent, the most Merciful. I would like to show my gratitude and thank the many people and organizations that helped me develop the idea into a reality.

First and foremost, I express my heartiest gratitude to my supervisor, Sir Talha, for his great interest, inspirable supervision, critique, valuable suggestions and encouragement in understanding and completion of my work. He has been a great source of inspiration with valuable insights. Moreover, i also would like to thank Syed Ali Bukhari and Mr. Khalil Arbi that guide me on my first research.

My gratitude is also due to all those Pre-Engineered Building Organization that took their time and effort to distribute the questionnaire among their project engineers.

I am also thankful to my fellow classmates for their constructive feedback and insightful comments.

I don’t have enough words to express my feelings about two special persons in my life, my parents, who are my inspiration in life and who made me what I am today. Their prayers always helped me out through ups and downs of my life.

RIZWAN KHURRAM

Abstract

The construction industry is more exposed to risk than other industry. If the risk is not handled properly it may causes the poor performance on the industry. Building projects scales are large in nature and they involved large amount of investment. Wastage of any resource influence is high loss in project. All the losses are associated with risk factors. In Pakistan, only few researches have been done so far in this area. Thus this study needs focus of risk management in field of construction projects. From study we conclude that financial issue, skillful workers, shortage and inaccurate design are significant risk factors affecting the projects. Contractors are responsible for risk linked with machinery, material and quality related issues. While clients is responsible for the risk associated with scope of work.  Study concludes that good coordination and communication between stakeholders and proper drawings works are key factors to control the project.

Contents

1	Introduction	1

1.1	Background of the Research	1

1.2	Risk	2

1.3	Technical Risk	3

1.4	Financial Risk	3

1.5	Management Risk	4

1.6	Project Risk Management	5

1.7	Significance of Risk Management	6

1.8	Difference between Pre-engineered buildings vs. conventional building	7

1.9	Pre Engineered Building	7

1.10	Research Problem	8

1.11	Objective of Research	8

1.12	Scope of study	9

2	Literature Review	10

2.1	Risk	10

2.2	Risk Identification	10

2.3	Design category	11

2.4	Finance category	13

2.5	Management category	14

Shortage of Skillful workers	14

Unknown site conditions	15

2.6	Construction project	16

2.7	Consultant	16

2.8	Contractor	17

3	RESEARCH DESIGN	23

3.1	Research Objective	23

3.2	Research Process	23

3.3	Risk in Pre Engineered Building	25

3.3.1	Technical Risk	25

3.3.2	Financial Risk	25

3.3.3	Management Risk	26

3.4	Theoretical Frame Work	26

3.4.1	Methodology	26

3.4.2	Method of Survey	27

3.4.3	Questionnaire Structure	27

3.5	Questionnaire Design	28

3.5.1	Risk Rating	28

3.5.2	PILOT STUDY	28

3.5.3	SAMPLING	29

4	ANALYSIS	30

4.1	Descriptive Analysis	30

4.2	Results of Analysis	31

4.3	Explanation	35

5	Conclusion	36

5.1	Few advices to the companies:	37

5.2	Suggestion for Future Work.	38

6	References	39

7	Appendices	45

7.1	List of Pre- Engineered Building Companies in Lahore.	45

7.2	Questionnaire	46

# Introduction

## Background of the Research

In order to meet stakeholder requirement, it is basically the implementation of all knowledge areas from where different tolls and technique are effectively utilized.

Project risk management includes the method of organize the context, identifying, analyzing, evaluating, treating, monitoring and responding to project risk associated with any activity. It consists of to increase the reaction of positive events or opportunity and minimizing the losses. Karatam and karatam in 2000 describe that the construction industries are directly linked with high degree of risk due to involvement of construction activities, organization environment, process.

Pre-Engineered Building concept is new in Pakistan; they need a lot of work to be done. Construction industry is more exposed of risk rather than other industry.  For every project in construction industry, risk management is an essential component of the process. From a client's perspective, design-bid-build is often the most risk adverse delivery method. But what about situations where time is short and structure must be optimized for space as well as cost savings. The greatest value in this case often lies in pre-engineered buildings.

As in IJEDR the PEB Structure is 30% lighter than conventional steel structure. As it reduces the dead load of structure so also reduces the size of foundations.

## Risk

In the book of PMI, Risk is a multifaceted concept. The construction industries business is more risky than others. However, construction projects are subjected to have more structural risks due to participation of different stake holders like suppliers, contractors, designers, owners etc.

Organizations face different types of risks depends upon the organization to organization. Mostly related to financial loss and business failure.

Risk can be explained as “the positive or negative impact on the objective that sometime happened. ” (Smith, 1999), “a combination of hazard and exposure” Chicken and Posner (1998). The construction industry business like any other business is more risky Because construction projects are more likely of inherent risks due to involvement of many contracting parties such as suppliers owners, designers ,contractors, etc. (PMI 2004).

Risks are either acceptable or unacceptable. An acceptable risk effect is on the non-critical path but on the other hand unacceptable risk is that negatively affect the on task on critical path. According to PMBOK the critical path is generally, but not always, the sequence of schedule activities that determine the duration of the project. It is the longest path through the project.

Generally the main types of risk are economical risk, financial risk, political and social risk, commercial and legal relationships, technical risk, and management risk

## Technical Risk

It is the ability to overcome the technological risks in construction projects. In this risk factors involves issues arise or concerns associated with the technologies involved in the exaction of construction projects. There are some technical risk which is very common in construction industry, like accident on site, change in the scope of design, failure of equipment, errors in drawings, and difficulty in construction at site. Shortage of electricity, material theft at site.  Lack of qualified staff, architecture or structure disputes.

## Financial Risk

Alaghbari in 2007 describe the financial risk as this type of category includes all the factors related to financial issues on the project, such as payment delayed, Problem of Cash flow, and external economic problems. Sweis and Aibinu describe the financial risk as it is the Major frame work of study shows that mostly finance-related risk factor is delayed payment for completed work. Major kind of risk includes loss due to inflation rate, due to fluctuation of interest rate, inflation of fuel price. Insurance risk, change of bank formalities and regulation.

## Management Risk

Heerkens describe the management risk as there are two important form of project management:  the science and the art of the project. The art deals with the stakeholder that are directly or indirectly involved in the project, while the science describe and coordinating the work to be done; for example, it concern with  the knowledge, skillful application and understanding of a project management process. Main management risks include change of top management, time constraints, and poor communication between clients. No expertise in similar projects.

## Project Risk Management

Standard Associates of Australia describe the project risk management as it is the processes culture and characterize structure that are towards the forceful management of potential opportunities and minimize the effects.

Kartam and Kartam in 2000 elaborate that construction industry business and its stakeholders are openly  associated with high degree of risks due to nature of construction business activities, organization, but the Edward in 1995 describe that construction industry has poor reputation in coping with risks, many projects fails to meet deadlines and cost targets. Clients, contractors, and other stakeholders the public and others have suffered as a result.

All choices in our life are having at risk. Risks cannot be totally eliminated, but have different choice that can be made so that it can be minimized.

Table 1.1 Project Risk Management

PM BOK,

## Significance of Risk Management

Following are the benefits of risk management (ISSN-2229-5518)

Less ambiguity

Formation of value

Accomplishment of objectives

Stakeholder’s reliability

## Difference between Pre-engineered buildings vs. conventional building

(IJEDR) Generally pre-engineered buildings are 30% lighter than conventional building due to efficient use of steel. Low frame weight give easy weight foundation design as well as higher resistance to seismic force as compared to conventional building which are higher in weight. Due to taper of the frame it increased the aesthetic view of the structure.

## Pre Engineered Building

Pre-engineered building is basically a steel structure that built by using the different components called as primary and secondary members. It is the cost effective alternate solution of conventional building. Members of primary structure are fabricated according to design requirement which save the cost and material. Construction time of PEB is faster than concrete construction.

For every project in construction industry, risk management is an essential element of  the process. From a client's perspective, design-bid-build is often the most risk adverse delivery method. But what about situations where time is short and structure must be optimized for space as well as cost savings. The greatest value in this case often lies in a PEB.

## Research Problem

What is the underline structure of project risk factors in Pre Engineered buildings in Lahore?

## Objective of Research

The construction industry is more exposed to risk than other industry. If the risk is not handled properly it may causes the poor performance on the industry. Building projects scales are large in nature and they involved large amount of investment. Wastage of any resource influence is high loss in project. All the loss are associated with risk factors

Risk management is basically the process of identifying the risk and mitigating the risk. In developed countries the research on risk assessment and its management has been done by various people. In Pakistan, only few researches have been done so far in this area. Thus this study needs focus of risk management in field of construction projects.

- To explore the project risk factors associated with  pre-engineered buildings in Lahore.

## Scope of study

Scope is restricted to the Pre Engineered Building construction industry and mainly covers the key stakeholder’s. Exercise has been made to include as many types of pre-engineered buildings projects as possible. Main city of Pakistan namely Lahore, was selected for questionnaire survey and interviews.

# Literature Review

## Risk

Risk is a multifaceted concept. The business of construction is more risky. Construction projects are exposed to more environmental and structural risks due to involvement of many stakeholders such as Designer, Supplier, and Contractor etc.

## Risk Identification

It is the main process of finding the risk which might affect the project and their characteristics (American National Standard 2004) and as per Standards Association of Australia 1999  it is the process of findings what can happen, why and how.

Proactive risk identification characterizes the potential future risk event that affect the result of objective positively or negatively. On the other hand reactive risk identification involves identifying and informs events, arising due to decision that could affect project objectives, either negatively or positively (Loosemore et al. 2006).

Past research literature will help in understanding and clarification of the topic and will help in development of Project Assessment and is management for this study to be conducted on the Pre-engineered building construction sector of Pakistan’s construction industry. The research can be summarized in an overall aim and measurable objectives. The aim is:

To explore the project risk factor associated with pre-engineered buildings projects in Lahore.

## Design category

The allocation of ample time and money at the begining level of design phase result into the minimization of time delay and cost overrun (Koushki et.al 2005). It is one of the important and critical because the factors related to it are considered to be key risks in construction project (Fereigh and kartam,2006).

It is the ability to overcome the technological risks in construction projects. In this risk factors involves issues arise or concerns associated with the technologies involved in the exaction of construction projects. There are some technical risk which is very common in construction industry, like accident on site, change in the scope of design, failure of equipment, errors in drawings, and difficulty in construction at site. Shortage of electricity, material theft at site.  Lack of qualified staff, architecture or structure disputes.

- Accidents on site

The ability to overcome the accident on site in construction projects. The risk factors having different issues or concerned associated with the accidents which cause loss of humans as well as money.

- Change in design

Koushiki describe the design risk as the allocation of ample time and money at the initial level of design phase result into the minimization of time delay and cost overrun. On the other hand Fereigh and karatam describe about the design category of risk it is one of the important and critical because the factors related to it are considered to be key risks in construction project.

- Errors in Drawing

The ability to overcome the errors issues in drawings. The risk factors involves issues and concerned associated with the drawings mistakes, which divert the scope of project.

- High degree of difficulty in construction

- The ability to overcome the difficulty in construction projects. The risk factors involves issues or concerned associated with the site execution which is not suitable for the Equipment Failure

The ability to overcome the equipment failure of the project. Mostly risks are associated with the failure of equipment that caused delays in project

Workers like raining, mountainous areas, irregular surface etc.

- Shortage of Electricity

The ability to overcome the shortage of electricity in construction projects. The risk factors involves issues or concerned associated with the equipment operations with electricity, which is now a day’s biggest issue arise in our country,

- Theft material at site

For the cheapest material a large number of   costs of projects is driving that meets specifications, which is to be fabricated in a location where that has the least cost- often in different countries.

- Architectural Vs. structural Engineering Disputes

The ability to overcome the disputes construction projects. Rrisk factors include issues or concerned associated with the architecture drawing and structural drawing.

- Site distance from urban Areas

The ability to overcome the difficulty in construction projects. The risk factors involve issues concerned associated with the far place areas.

- Lack of qualified staff

The ability to overcome the lack of qualified staff projects. The risk factors involves issues or concerned associated with the staff which has no past experience related to project.

## Finance category

This type of category includes all the factors related to financial issues such as cash flow problems, economic problems, payment delayed etc. (Alaghbari et al., 2007). Major frame work of study shows payment delayed related are the financial related risk factors for completed work (Sweis et al., 2008) and (Aibinu and Odeyinka, 2006).

- Bankruptcy of Project Stakeholder

- Loss due to Inflation rate

Inflation rate risk is more than other risk in case of financial risk, Because Pakistan is the developing country and the price of any material is not stable and the variations occur throughout the years.

- Loss due to fluctuation of interest rate

Interest rate fluctuation is also the one of the cause of financial risk.

- Loss due to inflation of fuel price
Fuel price is not same throughout the years, so such type of risk occurs in every project.

- Low credibility of shareholders and lenders

- Insurance risk

- Change in bank formalities and regulation

## Management category

There are two important form of project management:  the science and the art of the project. The art deals with the stakeholder that are directly or indirectly involved in the project, while the science describe and coordinating the work to be done; for example, it concern with  the knowledge, skillfull application and understanding of a project management process (Heerkens, 2001).

- Change of Top management

- Time constraints

- Poor communication between clients

- No previous experience in identical projects

- Poor Coordination, Cooperation and Relationship among Key Stake Holders

- Internal management problems

- Conflict in Contract Document

- Delays due to disputes with contractor

Shortage of Skillful workers

Shortage of skillful workers is the main cause of managerial risk factors, because PEB is the new field especially in Pakistan, and it has shortage of skillful workers

Material shortage
            shortage of material at site causes the delays of project; the works at site will stop. In PEB the assembly of frame are in systematic way, so if discontinuous occurs, that caused the delay of project and increase the cost of project as well.

Unknown site conditions
	unknown conditions of site produces difficulty in construction, it is better for having open site because movability of crane, and much more difficult where the access of crane is not possible.

Incompetence of transport facility

Such type of risk are also occurs in these building due large size of primary structure, rafter and columns.

Material category

This is an important category that directly effects on cost and delayed of any project. Major risk factors include in material categories are type of material, selection time and their availability in local market. Project activities that are relevent to material and their effect on total cost of project could be important (Manavazhi and Adhikari, 2002).

External category

External risk is not as such important as other risks because it doesn’t contribute any role in delayed of project (Sugiharto and Keith, 2003). Most of risk management studies show that external risk including weather and site condition creates a less impact on completion of project (Alaghbari et al., 2007).

Labor and equipment category

Labor risk include the factors of unavailability of workforces, unskillful labour, it is directly linked with the problems related to manpower. Whereas equipment factors related to reliability, availability and quality of equipment (Sweis et al., 2008).

## Construction project

According to (Levy, 2000) some important steps are necessary for construction projects to accomplishment which is following as,

- Completion of project on time.

- Total amount is within the budget.

- No allegation after Completion of Project

- Keep favorable relations with the stakeholder

- Quality level

Many stakeholders are involved in the construction project however the main construction parities are

Akintola S Akintoye and Malcolm J MacLeod (1997) concluded that risk management is necessary to construction business activities in minimizing losses and enhancing profitability. Construction risk is generally recognized as events that superimposed project objectives constraints (cost, time and quality).

Risk analysis and management in construction depend mainly on intuition, judgment and experience. Formal risk analysis and management techniques are rarely used due to a lack of knowledge and to doubts on the suitability of these techniques for construction industry activities.

The construction industry and its client are widely associated with high degree of risks due to nature of construction business activities, processes, environment and

Organizations (Kartam and Kartam 2000),

Edwards, L. (1995) Risk management is basically meant for reducing adverse effects on company's profitability. It is utilized to reduce long-term losses and hence increase profitability of the company.

Akintoye, A. S., & MacLeod, M. J. (1997) Risk management is crucial to construction activities as it reduces the loss and increases profits. It covers the effects of objectives of cost, time and quality. It mainly depends on experience, knowledge and intuitive judgment.

Perry, J. G., & Hayes, R. W. (1985, June) Risk Management is good during strategy, tender, development of contract preparation phases and its application stages. Risk management is primarily carried out to avoid cost and time overruns.

Edwards, P. J., & Bowen, P. A. (1998) Literature from 1960 to 1997 is reviewed to identify lags and inconsistencies in the knowledge of risk management in construction. Findings led to the suggestion that political, financial and cultural categories require more research attention than those related with QA and safety.

Bing, L., & Tiong, R. L. (1999) Risk management in JVs with a local partner is associated with  partner selection, employment, subcontracting, agreement, renegotiation and good relationship. Risk Management model would help construction firms to improve decision making and their ventures.

Tah, J. H. M., & Carr, V. (2000) Usual risk management techniques available to help construction industry to rise from poor performance are based on operational research techniques developed in 1960s of which most failed. Qualitative risk assessment has been tried as a model and its consequences are represented as fuzzy logic and cause and effect diagram.

Mulholland, B., & Christian, J. (1999) Construction projects are surrounded by the environment of high uncertainty and risk and are compounded by demanding time constraints. Knowledge and experience are required to make decision technique and amount of risk involved.

Baker, S., Ponniah, D., & Smith, S. (1999) Identification, analysis, evaluation, response and monitoring are important in the success of a project. Experience and engineering judgement are most applicable and favorable qualitative techniques and net present value, sensitivity and decision analysis are major quantitative techniques.

Kangari, R. (1988) For solving complex problems related to contruction management, a systematic approach is to be followed. A knowledge system consisting of applications of fuzzy sets, database and knowledge-base systems in construction risk management.

Ren, H. (1994) Two different elements are distinguished between concealment and action project risks and using risk relationships, mutual effects between risks are analysed.

Uher, T. E., & Toakley, A. (1999) A survey was conducted with the respondents who were familiar with risk management and it was statistically analyzed. The analysis revealed that the application of risk management in conceptual phase of the construction project was quite low.

Tah, J. H. M., & Carr, V. (2000) A common language is developed for description of risk and and remedial actions. UML and IDEF0 have been used to develop models which are used to facilitate the production of working risk management system.

Ranasinghe, M. (1998) A probability framework is developed to analyze the risk management procedure adopted by an insurance firm. The acceptable clients are those for which the probability of claim is 12% and those with over 50% the clients are not acceptable. The insights are extracted from project duration and costs.

Zhang, W. R., WANG, S. Q., TIONG, R. L., Ting, S. K., & Ashley, D. (1998) In china buil-operate-transfer (BOT) arrangement is prevailing to fulfil the requirements of China's economic growth and development. China's embryonic legal structure poses many risks and problems at the construction business. This paper sheds lights on risk allocation, government gaurantees and structuring of risk in BOT transport project.

Flanagan, R., Kendell, A., Norman, G., & Robinson, G. D. (1987) In construction industry, risk management term is generally used for future forecasting of the life cycle costs, e.g., maintenance and running cost. It is fairly known that all these cost estimated are merely guess-work. To challenge this view, some practical techniques addressing risk and uncertainty should be developed so that the stake holders can be provided with clear easy to understandable information, on which they can decide better.

Ashley, D. B., & Bonner, J. J. (1987) Political risk management and measurement is vital for international construction industry. International construction contracting are more vulnerable to politcal environments ehich directly impacts on cash-flow elements of their projects. An approach is devised in this paper to fill the gap which is made by traditional political risk analysis used by contracting firms.

Niwa, K., & Okuma, M. (1982) This paper uses 'know-how transfer method' and demonstrates its application for risk management system for a large scale construction project so that the project manager can get more effective control of risks in a systematic way.

Wang, S. Q., Tiong, R. L., Ting, S. K., & Ashley, D. (1999) China is attracting international investments for infrastructure development. It is necessary to manage and pinpoint risks involved in investing in China's BOT power projects. This paper throws light on the results of survey conducted with international professionals and suggests a framework for risk management for future investment in BOT projects in China.

Ward, S. C., & Chapman, C. B. (1991) A widespread definition of risk analysis is acquired to properly identify, appreciate and manage project risks. In contracting projects, the risk of project can be allocated properly.

Roger Miller described the understanding and managing risk in large engineering projects in international journal of project management. Firstly risk are needed to be classified into groups like market related, completion and institutional. Risk frame work not must be technical problem they will also a problem with managerial issue. Finally the danger risk only be tackle by influencing driver and institutions which leads the risk upward.

Martin Calaudia Garrdio on risk identification technique brief that they are a lot of methods to identify the risk in construction industries in Brazil. According to the result of identification techniques used in construction industries are check list, flow chart and brainstorming. These techniques are widely used in construction industries.
	Nur Alkaf Abd karim described that the risk is key role for the success of any project. His study is based upon the constructive perspective. He developed the 25 common factors of risk generally categorized into five factors. In the end he concluded that five most important factors. Shortage of material, insufficient technology, late delivery of material, poor quality of workman ship.

Tah, J. H. M., & Carr, V. (2000) Usual risk management techniques available to help construction industry to rise from poor performance are based on operational research techniques developed in 1960s of which most failed. Qualitative risk assessment has been tried as a model and its consequences are represented as fuzzy logic and cause and effect diagram.

Kangari, R. (1988) For solving complex problems related to contruction management, a systematic approach is to be followed. A knowledge system consisting of applications of fuzzy sets, database and knowledge-base systems in construction risk management.

Ren, H. (1994) Two different elements are distinguished between concealment and action project risks and using risk relationships, mutual effects between risks are analysed.

Uher, T. E., & Toakley, A. (1999) A survey was conducted with the respondents who were familiar with risk management and it was statistically analyzed. The analysis revealed that the application of risk management in conceptual phase of the construction project was quite low.

# RESEARCH DESIGN

## Research Objective

The construction industry is more exposed to risk than other industry. If the risk is not handled properly it may causes the poor performance on the industry. Building projects scales are large in nature and they involved large amount of investment. Wastage of any resource influence is high loss in project. All the loss is associated with risk factors

In developed countries the research on topic of risk management has been done by different people. In Pakistan, only few researches have been done in this area. Thus this research needs focus of risk management in field of construction.

- To identify the managerial risk in pre-engineered steel construction projects.

- To identify the financial risk in pre-engineered steel construction projects.

- To identify the technical risk in pre-engineered steel construction projects.

## Research Process

The large scale project involves heavy investment and funds so any type of wastage (either time, resources etc.) and associated with the different risk. In developed countries the research on risk management has been done by various people in the field of construction.

There have been many researches on different aspects of risk management and also on PEB projects. But there is need to further research on different aspects of application of risk management in PEB project domain. Risk management have been applied in PEB projects but how effectively it can be applied and which risk are more important to manage it should be research. So Objectivism epistemology is applied.

Different aspects of application of risk management in PEB projects can be understand through experience or examine risk management practically in PEB project. So this lead to Positivism theoretical perspective.

Examination of different examples or survey is required to practically understand the application of risk management in PEB projects. So this lead to survey research methodology.

In order to understand different aspects of risk management in PEB projects collection of data through questionnaire from practical examples or by sampling and quantitative analysis on them is required.

## Risk in Pre Engineered Building

### Technical Risk

- Change in Design

- Errors in Drawing

- Shortage of Electricity

- Theft material at site

- Accidents on site

- Architectural Vs. structural Engineering Disputes

- Lack of qualified staff

- Equipment Failure

### Financial Risk

- Inflation Rate

- inflation of fuel price

- Insurance risk

- fluctuation of interest rate

### Management Risk

- Change of Top management

- Poor communication between clients

- None previous experience in similar projects

- Poor Coordination, Cooperation and Relationship among Key Stake Holders

- Internal management problems

- Conflict in Contract Document

- Delays due to conflict with contractor

## Theoretical Frame Work

### Methodology

The methodology use in this project is given below.

- Study Risk Management and literature

- Formation of questionnaire

- Construction site visit

- Questionnaire surveys and interviews

- Analyzing the questionnaire

- Qualitative analysis  the data

- Conclusion

### Method of Survey

Methodology of this study depends on the survey conducted. The questionnaire collected from different contractor of different size through different resources like mail, meetings. Initially literature view was conducted to identify the major risk identification factors in PEB.

### Questionnaire Structure

Firstly Questionnaire was tested through pilot study which tells us the value of information, clarity and its ease. The Structure of questionnaire is shown in Appendix.

Associated risk Factors in PEB are given below:

- Financial risk

2.       Management risk

3.       Technical risk

## Questionnaire Design

The survey questionnaire is to design the study behavior of risk in Pre Engineered Building. Questionnaire was prepared through pilot survey according to their literature review in the field of construction. Free to ask extra questionnaire that arise in the mind of interviewer during interview.

### Risk Rating

For the rating of risk in construction industry, a likert scale of 1-5 is used. It is a type of psychometric response scale usually used in questionnaires and mostly used in survey research. Likert scale is named after Rensis Likert, who published a report describing its use (likert, 1932).

### PILOT STUDY

In the pilot survey questionnaire were conducted with the local contractors and follow-up interviews in the first phase. The purpose of the survey was to identify the risk factors.

The purpose of pilot studies to shortlist the relevant factors. By considering the construction industry for full survey, only selects the factors which are more relevant and important

### SAMPLING

Pre-Engineered Buildings Companies in Lahore were analyzed as the target population for PEB research. Approximate Eleven organizations working in Lahore were analyzed as sample for research. PEB companies in Lahore were randomly selected for this research. Reasons for using random sampling are making statistical inferences, achieving a sample and minimum their sampling bias. Random sampling was applied because the purpose of the simple random sample is to reduce or eliminate the possible for human bias in the selection of cases to be add in the sample. As a result, the simple random sample provides us with a sample that is highly representative of the population being studied, assuming that there is limited missing data. Best thing about random sampling is the ease of assemble the sample. The way of selection is considered fair from given population because every candidate is given equal chances of being selected (Bryman, 2012).

These organizations people worked in a project as leading role (Technical Person) were selected for data collection. Organizations with Project management unit were preferred for this research.

Project managers were asked to fill questionnaire in face to face meeting. Thoroughly discussions were also done with them on their project management experience for validation of results. Different questions which represent technical, managerial and financial risk associated with PEB are discussed and project managers inputs were marked on Likert scale. Data for different demographic features like qualification, experience was also gathered from project managers.

# ANALYSIS

## Descriptive Analysis

Statistical result analysis of empirical data collected through the questionnaire has been discussed below. Firstly, descriptive data analysis for all variables data has been done. Then, construct validity analysis for examine relationship between different risk factors has been done. After that check the instrument validity checked

Tables and graphs for SPSS analysis have been presented in appendix.

## Results of Analysis

Factor Analysis

| KMO and Bartlett's Test |  |  |
| --- | --- | --- |
| Kaiser-Meyer-Olkin Measure of Sampling Adequacy. |  | .728 |
| Bartlett's Test of Sphericity | Approx. Chi-Square | 503.544 |
|  | Df | 21 |
|  | Sig. | .000 |

| Communalities |  |  |
| --- | --- | --- |
|  | Initial | Extraction |
| Technicial Drawing | 1.000 | .823 |
| Managerial Team Conflicts | 1.000 | .645 |
| Managerial schedule error | 1.000 | .739 |
| Financial-loss inflation rate | 1.000 | .859 |
| Financial loss intrest rate | 1.000 | .886 |
| Managerial shortage of skillful | 1.000 | .507 |
| Managerial poor communication | 1.000 | .683 |
| Extraction Method: Principal Component Analysis. |  |  |

| Total Variance Explained |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component | Initial Eigenvalues |  |  | Extraction Sums of Squared Loadings |  |  | Rotation Sums of Squared Loadings |  |  |
|  | Total | % of Variance | Cumulative % | Total | % of Variance | Cumulative % | Total | % of Variance | Cumulative % |
| 1 | 3.926 | 56.091 | 56.091 | 3.926 | 56.091 | 56.091 | 3.779 | 53.982 | 53.982 |
| 2 | 1.216 | 17.375 | 73.466 | 1.216 | 17.375 | 73.466 | 1.364 | 19.484 | 73.466 |
| 3 | .847 | 12.101 | 85.567 |  |  |  |  |  |  |
| 4 | .457 | 6.526 | 92.093 |  |  |  |  |  |  |
| 5 | .309 | 4.409 | 96.503 |  |  |  |  |  |  |
| 6 | .178 | 2.544 | 99.046 |  |  |  |  |  |  |
| 7 | .067 | .954 | 100.000 |  |  |  |  |  |  |
| Extraction Method: Principal Component Analysis. |  |  |  |  |  |  |  |  |  |

| Component Matrixa |  |  |
| --- | --- | --- |
|  | Component |  |
|  | 1 | 2 |
| Technicial Drawing | .891 |  |
| Managerial Team Conflicts | .773 |  |
| Managerial schedule error | .859 |  |
| Financial-loss inflation rate | .922 |  |
| Financial loss intrest rate | .899 |  |
| Managerial shortage of skillful |  | .625 |
| Managerial poor communication |  | .812 |
| Extraction Method: Principal Component Analysis. |  |  |
| a. 2 components extracted. |  |  |

| Rotated Component Matrixa |  |  |
| --- | --- | --- |
|  | Component |  |
|  | 1 | 2 |
| Technicial Drawing | .826 |  |
| Managerial Team Conflicts | .803 |  |
| Managerial schedule error | .831 |  |
| Financial-loss inflation rate | .919 |  |
| Financial loss intrest rate | .939 |  |
| Managerial shortage of skillful |  | .688 |
| Managerial poor communication |  | .825 |
| Extraction Method: Principal Component Analysis. Rotation Method: Varimax with Kaiser Normalization. |  |  |
| a. Rotation converged in 3 iterations. |  |  |

| Component Transformation Matrix |  |  |
| --- | --- | --- |
| Component | 1 | 2 |
| 1 | .972 | .233 |
| 2 | -.233 | .972 |
| Extraction Method: Principal Component Analysis. Rotation Method: Varimax with Kaiser Normalization. |  |  |

Reliability

Scale: ALL VARIABLES

| Case Processing Summary |  |  |  |
| --- | --- | --- | --- |
|  |  | N | % |
| Cases | Valid | 105 | 100.0 |
|  | Excludeda | 0 | .0 |
|  | Total | 105 | 100.0 |
| a. Listwise deletion based on all variables in the procedure. |  |  |  |

| Reliability Statistics |  |
| --- | --- |
| Cronbach's Alpha | N of Items |
| .850 | 7 |

| Item-Total Statistics |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Scale Mean if Item Deleted | Scale Variance if Item Deleted | Corrected Item-Total Correlation | Cronbach's Alpha if Item Deleted |
| Technicial Drawing | 19.63 | 14.678 | .841 | .803 |
| Managerial Team Conflicts | 20.65 | 14.711 | .639 | .824 |
| Managerial schedule error | 20.70 | 12.749 | .776 | .801 |
| Financial-loss inflation rate | 20.56 | 11.922 | .840 | .788 |
| Financial loss intrest rate | 21.20 | 13.604 | .782 | .801 |
| Managerial shortage of skillful | 19.76 | 17.491 | .279 | .869 |
| Managerial poor communication | 20.35 | 18.769 | .110 | .881 |

## Explanation

Data description analysis for all variables explains following features.

- Exploratory factor analysis has been used as a technique of data analysis.

- Principle component analysis method is used

- Rotation Method of varimax with Kaizer Normalzation

- Total dimension are taken is seventeen.

- Dimensions are to be eliminated on the basis of two.

- Dimensions having factor loading are less than  0.4 are eliminated

- Dimension having cross loading on multiple factors were eliminated

- Total factor selected for reliability is 7 and in result their Cronbach’s Alpha value is 0.850. That shows the reliability of the dimensions is okay.

# Conclusion

The word risk management is new in construction factors especially in PEB in Pakistan. As Pakistan is in the list of developing country so it should be updated. Following are the some points extracted from  thesis.

- . Shortage of workers is considered to be the main problem faced by all companies. The main reason is shuffling of workers due to their high demand. As demand and salary package of Middle East countries is handsome as compared to Pakistan,  So Most of the workers wanted to shift there.

- Inflation rate is changes with time which is very high in our country. So the prices and material and their related material varies with passage of time. The effect of inflation is directly on construction firms, land developers and stakeholders. Financial part risk is very high as compare to others because bank also increase their interest rate

- In sum up of all risk, especially in PEB industries Technical, managerial and financial risk are dominant than other risks.

## Few advices to the companies:

- From different survey, we analyses that risk management technique is not properly and efficiently utilized  in most of the construction companies. But it should be keep as primary tool to assess the project. if risk occurs , no any prompt action techniques is in place to mitigate.

2.  Financial risk is not handling by engineers alone so it should be handle carefully using financial consultant.

3.   There is even no single manager who handles risk management in organization and takes decision accordingly. So risk management body should be formed and evaluation should be done at least once in a month.

4.  Companies management hierarchy is more important to follow the employee’s voice. Top to bottom ways is traditional but down to top should be followed so that employee’s voice is heard.

5.   It is more useful to include a risk consultant in a project by considering the stakeholder

## Suggestion for Future Work.

We have some suggestion and recommendation for the construction industries working in Pakistan are stated below.

- As this study is organize in Pre Engineered building construction projects sectors of Lahore. It can also be organize in other region and cities.

- Additional this study can also be conducted on different risk factors associated with PEB.

- Investigate further risk management topic related to the construction industries.

# References

Akintoye, A. S. and Macleod, M. J. (1997). “Risk analysis and management in construction” International Journal of Project Management, 15(1), 31-38.

Aleshin, A. (2001). “Risk management of international projects in Russia” International Journal of Project Management, 19(4), 207-222.

AIBINU, A. A. & ODEYINKA, H. A. 2006. Construction Delays and Their Causative  Factors in Nigeria. Journal of Construction Engineering and Management, 132,

Artto, K. A.  (1997). “Fifteen uears of project risk management applications-where are we going?”, Proceeding of IPMA symposium of project management, Helsinki: E&FN Spon, pp. 3-14.

Assaf, S. A. and Al-Hejji, S. (2006). “Causes of delay in large construction projects” International Journal of Project Management, 24(4), 349-357.

AS/NZS 4360. (1999). “Australian/ New Zealand standard on risk management” Standards Australia and Standards New Zealand.

Bajaj, D., Oluwoye, J. and Lenard, D. (1997). “An analysis of contractor’s approach to risk identification in New South Wales, Australia” Construction management and economics, 15(4), 363-369.

Baker, S., Ponniah, D. and Smith, S. (1999) “Risk response techniques employed currently for major projects” Construction management and economics, 17(2), 205-213.

Chicken, J. C. and Posner, T. (1998). “The Philosophy of risk” Thomas Telford.

Cooper D. R, and Schindler P. S. (2001). “Business research methods” International edition, Mcgraw-Hill.

Edwards, L. (1995). “Practical risk management in construction industry” Thomas Telford, London.

El-Sayegh, S. M. (2007). “Risk assessment and allocation in UAE construction industry” International Journal of Project Management , 26(4), 431–438

El-Sayegh, S. M. (2008). “Risk assessment and allocation in UAE construction industry”, International Journal of Project Management, 26(4), 413438.

Faber, W. (1979). “Protecting giant projects: A study of problems and solutions in the area of risk and insurance”, Willis Faber, England, Ipswich, UK.

Fisk Edward, R. “Construction project administration” Risk allocation and liability sharing 4th.Ed., 1992, pp. 217-233

Flanagan, R. and Norman, G. (1993). “Risk management and construction” Blackwell Scientific, Oxford, UK.

Fowler, A. and Walsh, M. (1999). “Confliction perceptions of success in an information system project”, International Journal of Project Management,17(1),1-10.

Gupta, J. P. and Sravat, A. K. (1998). “Development and project financing of private power projects in developing countries: a case study in India” International Journal of Project Management, 16(2), 99-105

Hameed, A., and Woo, S. (2007). “Risk importance and allocation in Pakistan construction industry: A Contractor’s perspective” KSCE Journal of Civil Engineering, 11(2), 73-80.

Hertz, D. B. and Thomas, H. (1983). “Risk analysis and its applications” John Wiley and Sons, Inc., New York.

Henery, G. T. (1990). “Practical Sampling” Newburg park: Sage publications.

Jaafari, A. (1999). “Management of risks, uncertainties and opportunities on projects: time for a fundamental shift” International Journal of Project Management, 19(2), 89–101.

Kangari, R. (1995).  “Risk Management perceptions and trends of US construction”,Journal of Construction Engineering and Management, 121(4), 422-429.

Kartam, N. A., and Kartam S. A. (2000). “Risk and its management in the Kuwaiti construction industry: a contractors’ perspective” International Journal of Project Management, 19(6), 325–335.

Kumeraswamy, M.M, Palaneeswaran, E. and Humphreys, P. (2000).  “Selection metters in construction chain optimization”, International Journal of Physical Distribution in Logistics Management, 30(7/8), 661-68

Ling, F. Y. Y. and Hoi, L. (2006). “Risks faced by Singapore firms when undertaking construction projects in India”, International Journal of Project Management, 24(3), 261-270.

Loosemore, M.(2000).  “Crises management in construction projects” American society of civil engineers press, New York, USA.

Loosemore, M., Raftery, J., Reilly, C. and Higgon, D. (2006). “Risk Management in Projects” 2nd. Ed., Taylor & Francis, New York. p.157 .

Luu, V. T., Kim, S. Y., Tuan, N. V. and Agunlana, S. O.  (2009). “Quantifying schedule risk in construction projects using Bayesian belief network”,International Journal of Project Management, 27(1), 39-50.

Lyons, T. and Skitmore, M. (2004). “Project risk management in queensland engineering construction industry: A survey” International Journal of Project Management, 22(1),51- 61.

Miller, R., & Lessard, D. (2001). Understanding and managing risks in large engineering projects. International Journal of Project Management, 19(8), 437-443.

Mills, A. (2001). “A systematic approach to risk management for construction” Structural survey, 19(5), 245-252.

Morris, P.W.G. and Hough, G.H. (1987).  “The anatomy of major project”, Wiley, NewYork.

Okmen, O. (2002).  “Risk analysis and management of construction projects tendering under design-build (Turnkey) contract system”, MSc Thesis, University of Gaziantep, Gaziantep.

Ozdoganm, I. D. and Birgonul, M. T. (2000). “A decision support framework for projects sponsors in planning stage of BOT projects” International Construction management and economics, 18(3), 343-353.

Oztas, A. and Okmen, O. (2004). “Risk analysis in fixed price design-build construction projects”, Building and environment, 39(2), 229-237.

Oztas, A. and Okmen, O. (2005). “Judgmental risk analysis process development in construction projects”, Building and environment, 40(9), 1244-1254.

Pender, S. (2001). “Managing incomplete knowledge: Why risk management is not sufficient” International Journal of Project Management, 19(2), 79-87.

Perry, J. G., and Hayes, R. W. (1986). “Risk and its management in construction projects” Proceeding of Institution of Civil Engineers, 4(4), 211-216

PMI. (2004). “A guide to project management body of knowledge 3rd.Ed.” Project management institute Inc., USA.

Rowe, W.D. (1977). “Protecting An anatomy of risk”, New York, Wiley. Sambasivan, M., and Soon, Y. W. (2006). “Causes and effects of delays in Malaysian

construction industry” International Journal of Project Management, 25(5), 517-526.

Shen, L. Y. (1997). “Project risk management in Hong Kong” International Journal of Project Management, 15(2), 101-105.

Shen, L. Y. (2007). “Project risk management in Hong Kong” International Journal of Project Management, 15(2), 101-105.

Smith, N. J. (1999). “Managing risk in construction projects” Blackwell, Oxford.

Songer, A. D.,Diekmann, J. and Pecsok, R. S. (1997). “Risk analysis for revenue dependent infrastructure projects” Construction Management and Economics, 15, 377-82.

Thomas, P. and Perry, J. (1992).  “Engineering construction risks.: a guide to project risk analysis and risk management”, Thomas Telford, London.

Tobani, M. (1999) “Private infrastructure, public risk” Finance and developement, 36(1).

Wang, S. Q., Dulaimi, M. F. and Aguria, M. Y.  (2004).  “Risk Management framework for construction projects in developing countries”, Construction Management and Economics, 22(3), 237-252.

Wang, S. Q., Tiong, R. L. K., Ting, S. K. and Ashley, D.  (2000).  “Evaluation and management of foreign exchange and revenue risks in China’s BOT projects”, Construction Management and Economics, 18(2), 197-207.

Yeo, K. T. and Tiong, R. L. K. (2000) “Positive management of differences for risk reduction in BOT projects” International Journal of Project Management, 18(4), 257-265.

Zhi, H. (1995). “Risk management for overseas construction projects” International Journal of Project Management ,13(4), 231-237.

Zou, X. W., Zhang, G., and Wang, J. (2007). “Understanding the key risks in construction projects in China” International Journal of Project Management, 25(6).

# Appendices

## List of Pre- Engineered Building Companies in Lahore.

- Rhino Pre-Engineered Buildings

- Izhar Steel (Pvt.) Ltd.

- Banu Mukhtar Steel (Pvt.) Ltd

- Fabcon Design & Engineering (Pvt.) Ltd.

- Hh Robertson

- Zamil Steel

- Kirby Building Systems

- Mammut Building Systems

- Peb Steel

- Metallic Solutions

- Reco Steel Building System

- Premium

## Questionnaire

| Name |  |
| --- | --- |
| Experience in PEB Industry (Years) |  |
| Organization / Department / Firm / Company |  |

| Sr.NO | Technical risk is considered as an important threat to PEB Projects. Please indicate or mentioned the degree of importance of each of the below mentioned Technical risk likely to occur during the entire life cycle of PEB Projects in Lahore, Pakistan. | 1 = Not important, 2 = Lightly Important 3 = Neutral 4 = Very Important 5 = Extremely Important |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 |
| 1 | Change in design scope |  |  |  |  |  |
| 2 | Equipment failure |  |  |  |  |  |
| 3 | Drawing or Detailing Error |  |  |  |  |  |
| 4 | Shortage of Electricity |  |  |  |  |  |
| 5 | Architecture / Structure Disputes |  |  |  |  |  |
| 6 | Material Theft |  |  |  |  |  |

| Sr.NO | Managerial risk is considered as an important threat to PEB Projects. Please indicate or mentioned the degree of importance of each of the below mentioned Managerial risk likely to occur during the entire life cycle of PEB Projects in Lahore, Pakistan. | 1 = Not important, 2 = Lightly Important 3 = Neutral 4 = Very Important 5 = Extremely Important |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 |
| 1 | Change in Top management |  |  |  |  |  |
| 2 | Project team Conflicts |  |  |  |  |  |
| 3 | Scheduled errors, contractor delays |  |  |  |  |  |
| 4 | Poor Coordination, Cooperation and Relationship among Key Stake Holders |  |  |  |  |  |
| 5 | Shortage of skillful workers |  |  |  |  |  |
| 6 | Poor Communication between Clients |  |  |  |  |  |

| Sr.NO | Financial risk is considered as an important threat to PEB Projects. Please indicate or mentioned the degree of importance of each of the below mentioned Financial risk likely to occur during the entire life cycle of PEB Projects in Lahore, Pakistan. | 1 = Not important, 2 = Lightly Important 3 = Neutral 4 = Very Important 5 = Extremely Important |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 |
| 1 | Inflation rate loss |  |  |  |  |  |
| 2 | Interest rate loss |  |  |  |  |  |
| 3 | Rise in fuel price loss |  |  |  |  |  |
| 4 | Incomplete or inaccurate cost estimate. |  |  |  |  |  |
| 5 | Exchange rate loss |  |  |  |  |  |